## Traxia TPMS
| Traxia TPMS |  |  |  | Last Update : | 2016-11-02
| Features | Status |  | Outstanding | Target | Note
Onboard Hardware | Main Hardware | Complete | 100%
| Customized Data Cable to OHT | Complete | 100%
| Customized Bracket | Complete | 100%
Firmware
| Capture TPMS data | Improvement | 90% | Cycle time modul | W2 Nov | SCG Sukabumi
| RCM | Development | 80% | Data synchronization | W2 Nov | SCG Sukabumi
| Capture Machine Health Data | Development | 40% | Read machine data through CDL
Additional Hardware
| SMU Modul* | Complete | 100%
Connectivity | GSM/GPRS (Default) | Complete | 100%
| Wireless | Development | 80%
| Subscriber Site Server | Development | 40%
Monitoring & Reporting | Landing Dashboard Page
| Notification | Live | 100%
| Haul Road Rating | Development | 80%
| Avarage Loading Time Monitoring | Live | 100%
| Avarage Loaded/Empty Travel Speed | Live | 100%
| Production Monitoring | Live | 100%
Payload Overview Page & Reporting
| Payload management | Live | 100%
| Composite pressure limit | Live | 100%
| Payload distribution | Live | 100%
| Cycle time distribution | Live | 100%
| Load placement distribution | Live | 100%
Machine Health Overview Page
| Machine Health Parameters | Development | 50% | Displays the machine health
| Live Event | Development | 50% | Displays the live event
Active Mail Report
| Daily Executive Report | Live | 100%
| Weekly Executive Report | Live | 100%
| Monthly Executive Report | Live | 100%

## Traxia Marine
| Traxia Marine |  |  |  | Last Update : | 2016-11-02
| Features | Status |  | Outstanding | Target | Note
Onboard Hardware | Main Hardware (Default: 2 Engine) | Complete | 100%
| Customized Data Cable to Engine | Complete | 100%
| Customized GPS Cable | Complete | 100%
Firmware
| Capture Engine Health Data | Complete | 100%
| Capture Live Event | Complete | 100%
Additional Hardware
| Additional Engine Monitoring Modul for 3 Engine | Complete | 100%
| Additional Engine Monitoring Modul for 4 Engine | Complete | 100%
| Additional Engine Monitoring Modul for 5 Engine | Complete | 100%
Monitoring & Reporting | Map Display Page | Live | 100%
| Utilization Report Page | Live | 100%
| Trend Data Report Page | Live | 100%
| Diagnostic Report Page | Live | 100%
| Unit Tracking History Page | Live | 100%
| Live Dashboard Page | Live | 100%
Active Mail Report
| Daily Executive Report | Live | 100%
| Weekly Executive Report | Live | 100%
| Monthly Executive Report | Live | 100%
Administrator Page
| Trakindo Login (for all customer units-hierarchy) | Live | 100%
| Web Management (setting, config, etc) | Live | 100%
| Tracker Health Monitoring Dashboard | Live | 100%
Documentation & Support | Documentation
| Traxia Marine Project Document |  |  |  | 2016-11-02
| Installation |  |  |  | 2016-11-04
| Maintenance |  |  |  | 2016-11-04
| Troubleshooting |  |  |  | 2016-11-04
Training of Trainer (TOT)
| TOT for installation |  |  |  | W4 Nov
| TOT for troubleshooting |  |  |  | W4 Nov
| TOT for web service |  |  |  | W4 Nov
Service Support
| Vendor (DIT) PIC | Complete | 100% |  |  | Anugrah Ardani (ardani@dit.co.id)
| After sales support | Complete | 100% |  |  | 1x24 hours call support will be active and DIT prepare standby engineer to be deploy if call support is fail.
| Problem escalation |  |  |  | 2016-11-04 | Refer to troubleshooting document

## Traxia HMS
| Traxia HMS |  |  |  | Last Update : | 2016-11-02
| Features | Status |  | Outstanding | Target | Note
Onboard Hardware | Main Hardware | Complete | 100%
| Customized Data Cable to Machine | Complete | 100%
Firmware
| Capture Engine Health Data | Complete | 100%
| Capture Non-Engine Health Data | Complete | 100%
Monitoring & Reporting | Map Display Page
| Unit Location on Map (Google Map) | Live | 100%
| Detail Machine Movement (Mining Map) | Live | 100%
| Utilization Report Page | Live | 100%
| Trend Data Report Page | Live | 100%
| Diagnostic Report Page | Live | 100%
| Unit Tracking History Page | Live | 100%
| Custom Map Management | Live | 100%
| Live (BCS) Dashboard Page | Live | 100%
Active Mail Report
| Daily Executive Report | Live | 100%
| Weekly Executive Report | Live | 100%
| Monthly Executive Report | Live | 100%
Connectivity | Satellite option | Development | 80% |  | W1 Sept
| POC |  |  |  | done | 2016-08-30
| Send satellite modem to site |  |  |  | done | 2016-09-05
| Satellite modem installation on CE7141 |  |  | Onboard firmware haven't finished updated (out of GSM coverage) | done | 2016-09-13
| Satellite modem relocation to CE7144 |  |  | Onboard firmware (CE7144) have finished updated | WIP

## HiTren
[5 empty] | Last Update : | 2016-11-02 | Traxia TPMS
| Features | Status |  | Outstanding | Target | Note
Web NMS App | Main Hardware
| Design new hardware Hi-Tren & concentrator | Complete | 100%
| Development module/prototype Hi-Tren & Concentrator | Complete | 100% |  | 2016-10-18
| Testing module/prototype hardware | Complete | 100% |  | 2016-11-26 | no issues found
| Build & test hardware Hi-Tren & Concentrator | WIP | 100% |  | 2016-11-04 | real hardware: 3 Hi-Tren + 1 Concentrator
| Testing hardware at Depo Sewatama (Cakung) | Scheduled |  |  | 2016-11-11
Firmware
| Capture Engine/EMCP 3 data | Complete | 100%
| Capture data non EMCP: GCP, power meter, protection) | Complete | 100%
| Send control command (on, off, setpoint) via modbus | Complete | 100%
Server Engine | Hardware
| Hi-Tren NMS | WIP | 90% |  | 2016-11-11 | use Hariff server
Monitoring & Reporting | Landing Dashboard Page | WIP | 85% |  | 2016-11-11
| Monitoring | WIP | 85% |  | 2016-11-11
Reporting
| Trending data | WIP | 85% |  | 2016-11-11
| Export data to file | WIP | 85% |  | 2016-11-11
| Daily Activity Report | Complete |  |  |  | use desktop application
| Alert | WIP | 85% |  | 2016-11-11
| PM Schedule | WIP | 85% |  | 2016-11-11
Automatic email
| Monthly Executive Report | WIP | 85% |  | 2016-11-11
Web Administration | User management | WIP | 85% |  | 2016-11-11
| Customer registration | WIP | 85% |  | 2016-11-11
Equipment management
| Equipment registration | WIP | 85% |  | 2016-11-11
| Parameter management limit | WIP | 85% |  | 2016-11-11
Implementation | Site Survey | Complete | 100% |  |  | PLTD Ampenan 3; 11 unit Genset 3516
| Equipment preparation (cable, conduit, UPS, etc) | WIP |  |  | 2016-11-18
| Installation | Scheduled |  |  | 2016-11-28
| Monitoring | Scheduled |  |  | 2016-12-28
| Review | Scheduled |  |  | 2017-01-13